WORKPLAN

Targeted Evidence Review: Nutrition Interventions for LMICs

Deep-Dive on CMAM, Breastfeeding, and MMS

Prepared for: CARE International / ScaleWorks / IA Working Group

Prepared by: CEGA, University of California, Berkeley

Date: July 10, 2026

Timeline: 4 weeks (July 10 – August 8, 2026)

# 1. Background

In June 2026, CEGA delivered a rapid evidence synthesis covering 15 nutrition interventions for children under 5 and women of reproductive age in LMICs, ranked across evidence strength, cost-effectiveness, and scalability. The synthesis was produced using an automated two-phase evidence review pipeline (PubMed + OpenAlex retrieval, population-targeted scoring, full-text extraction, LLM-grounded synthesis with automated claim verification).

Following the IA working group meeting, CARE and partner organizations (Save the Children, Mercy Corps) reviewed the findings and converged on three interventions for a deeper, more targeted review:

- Community-based Management of Acute Malnutrition (CMAM/RUTF) — a health-system treatment package with innovation around simplified protocols, community-based approaches, and cost efficiency.

- Breastfeeding Promotion & Support — to be disaggregated into (a) facility-based support around delivery and (b) community/CHW postnatal counselling.

- Antenatal Multiple Micronutrient Supplementation (MMS) — a commodity-based intervention focused on the IFA-to-MMS transition, logistics, financing, and adherence.

A critical insight from the initial review and partner feedback: the evidence base for these interventions is well-established. The binding constraint is not efficacy but adherence, coverage, and sustainable operationalization. This deep-dive therefore expands the review scope beyond clinical endpoints to include implementation, scaling, and delivery-platform evidence.

# 2. Objectives

- Conduct a PICOS-structured evidence review for each of the three interventions, covering both clinical effectiveness and implementation/scaling outcomes.

- Disaggregate breastfeeding promotion into distinct intervention packages with separate evidence profiles (facility-based vs. community-based).

- Identify implementation barriers, delivery platforms, and country-level enabling conditions for scale-up.

- Produce a country shortlist (3–5 candidates) for potential co-design of a national-level intervention leveraging existing government infrastructure.

- Deliver a formatted review document to CARE and IA partners by early August 2026.

# 3. Scope: Interventions & PICOS Framework

Each intervention will be reviewed using a PICOS framework. Population and Outcome are scoped to children under 5 and WRA in LMICs but not fully restricted, to allow relevant adjacent evidence. The framework below will be refined during the background study (Week 1).

## 3.1 CMAM / RUTF

| PICOS | Scope |
| --- | --- |
| Population | Children 6–59 months with severe or moderate acute malnutrition in LMICs |
| Intervention | Community-based management (RUTF, simplified protocols, CHW-led detection/referral, combined prevention+treatment models) |
| Comparison | Standard facility-based SAM treatment; simplified vs. standard CMAM; combined vs. treatment-only |
| Outcomes | Recovery rate, relapse rate, case-fatality rate, coverage, cost per child treated, cost per DALY averted, program coverage, barriers to scale |
| Study types | Meta-analyses, systematic reviews, RCTs, implementation research, program evaluations, cost-effectiveness analyses |

## 3.2 Breastfeeding Promotion & Support (disaggregated)

Per partner feedback, this intervention is reviewed as two distinct packages:

### 3.2a Facility-based support

| PICOS | Scope |
| --- | --- |
| Population | Mothers and newborns at delivery and in the immediate postnatal period in LMICs |
| Intervention | BFHI (Baby Friendly Hospital Initiative), early initiation support, skin-to-skin contact, in-service/pre-service health worker training |
| Comparison | Standard maternity care without structured breastfeeding support |
| Outcomes | Early initiation rate, exclusive breastfeeding at discharge, EBF at 1/3/6 months, health worker competency, cost per mother-infant pair, implementation fidelity |
| Study types | Meta-analyses, systematic reviews, RCTs, quasi-experimental, implementation research, BFHI evaluations |

### 3.2b Community/CHW postnatal counselling

| PICOS | Scope |
| --- | --- |
| Population | Mothers and infants 0–24 months in community settings in LMICs |
| Intervention | CHW home visits, peer counsellors, mother-to-mother support groups, repeated-contact postnatal counselling, cash+SBCC for PLW |
| Comparison | Standard care (no structured community support); peer vs. CHW models; single vs. repeated contacts |
| Outcomes | EBF at 1/3/6 months, continued breastfeeding at 12/24 months, diarrhoea/ARI incidence, adherence to counselling visits, cost per contact, demand-side barriers (social norms, workplace) |
| Study types | Meta-analyses, systematic reviews, RCTs, quasi-experimental, implementation research, behavioral science |

## 3.3 Antenatal MMS

| PICOS | Scope |
| --- | --- |
| Population | Pregnant women in LMICs, particularly in settings with existing IFA programs |
| Intervention | UNIMMAP-type antenatal MMS (15 micronutrients); IFA-to-MMS transition programs |
| Comparison | Standard antenatal IFA; MMS vs. IFA (the policy-relevant comparison) |
| Outcomes | Low birth weight, SGA, preterm birth, neonatal mortality, maternal anaemia, adherence, cost per DALY averted, cost per pregnancy, supply chain feasibility, transition barriers |
| Study types | Meta-analyses, systematic reviews, RCTs, IPD meta-analyses, cost-effectiveness analyses, transition/implementation studies |

# 4. Methodology

This deep-dive builds on CEGA’s automated evidence review pipeline (v4), adapted for a more targeted, PICOS-structured search. The key methodological enhancements are:

- PICOS-targeted queries: search strategies are built from the PICOS framework rather than broad intervention-domain queries, increasing precision.

- Expanded outcome scope: implementation and scaling outcomes (coverage, adherence, cost-per-beneficiary, delivery platform feasibility, institutional barriers) are added alongside clinical endpoints.

- Implementation science inclusion: study type filters are broadened to include program evaluations, implementation research, and quasi-experimental designs alongside traditional MAs/SRs.

- Country-level evidence: country-specific queries or filters for the shortlisted candidate countries.

- Grounded synthesis: every numeric claim is cited to a corpus paper; cost-effectiveness rated only where a genuine CEA exists; automated claim verification.

The pipeline retrieves from PubMed and OpenAlex, deduplicates, scores, retrieves full text (PMC + Unpaywall PDF fallback), extracts per-study evidence cards, and synthesizes per intervention using LLM agents with hard grounding rules. A verifier lints every claim against the corpus.

# 5. Country Scoping

In parallel with the evidence review, we will identify 3–5 candidate countries for potential co-design of a national-level intervention. Selection criteria:

- High burden of malnutrition (stunting, wasting, or micronutrient deficiency) in children under 5 and/or WRA

- Existing government nutrition infrastructure (ANC platforms for MMS, community health systems for CMAM/BF, national fortification programs)

- IA partner presence and operational capacity (CARE, Save the Children, Mercy Corps)

- Policy openness to innovation (e.g., countries actively considering IFA→MMS transition, simplified CMAM protocols, BFHI scale-up)

- Availability of implementation/cost data in the evidence base

The country shortlist will be surfaced to CARE and partners for feedback before the model runs, so that country-specific queries can be incorporated into the review.

# 6. Timeline & Deliverables

| Week | Dates | Activities | Deliverables |
| --- | --- | --- | --- |
| 1 | Jul 10–17 | Akash conducts background study: review canonical studies, WHO protocols, country case studies for each intervention. Begin PICOS design. | Background briefs (draft). Country longlist. |
| 2 | Jul 17–24 | Akash finalizes PICOS. Begin pipeline adaptation (targeted queries, expanded study types, scoring adjustments). Surface country shortlist to CARE. | PICOS specification. Country shortlist (3–5). Pipeline queries ready. |
| 3 | Jul 24–31 | Akash fine-tunes model and runs: Phase 1 + Phase 2 per intervention. Full-text retrieval. Per-study extraction. Draft synthesis per intervention. | Per-intervention evidence DB. Draft synthesis sections. |
| 4 | Jul 31–Aug 8 | Liz reviews first pass. Akash incorporates feedback, reruns model if needed. Finalize country recommendation. Format and share. | Final deep-dive review document. Country recommendation. Shared with CARE. |

# 7. Final Deliverables

- Deep-dive evidence review document covering all 3 interventions (CMAM, Breastfeeding facility + community, MMS), with PICOS-structured findings, effect sizes, implementation evidence, and cost-effectiveness where available.

- Country shortlist with rationale and recommendation for co-design site.

- Per-intervention evidence database (structured, machine-readable) for further analysis. (If required)

- Background briefs summarizing the intervention landscape and canonical studies.

# 8. Team & Coordination

CEGA research team: Akash Shaji, Liz Brown